## Timesheet
Timesheet
| Daily | Weekly
Working hours/ Person | 7 | 42
Average Team Working hours / Member | 9.0542 | 54.325
|  |  | Week | Working Hours
Week | Working Hours |  | Week2 - Planning | 31
Week2 - Planning | 31 |  | Brainstorm on video presentation ideas | 2
Week3 - Project Presentation | 6 |  | Brainstorm Project Ideas | 2
Week 4 - Delivery Cycle 1 | 54.3 |  | Delivery Cycle Overview first version | 4
Week 5 - Delivery Cycle 1 / presentation | 13 |  | Delivery Cycle planning first version | 5
Week 5 - Delivery Cycle 2 | 61 |  | Draft System Overview Proposal Version 1 | 4
Week 6 - Delivery Cycle 2 | 52 |  | Functional Decomposition Diagram first version | 5
Grand Total | 217.3 |  | Functional Decomposition Diagram Second Version | 3
|  |  | Project decision | 1
|  |  | Researching | 5
|  |  | System Overview Proposal and planning | 0
|  |  | Week3 - Project Presentation | 6
|  |  | Executive overview | 4
|  |  | PowerPoint for the presentation | 2
|  |  | Week 4 - Delivery Cycle 1 | 54.3
|  |  | Main Functionalities in each level | 4
|  |  | Screen for returning user | 2
|  |  | About us’ content | 1
|  |  | Collect and Integrate data | 20
|  |  | Collect Tips and general facts | 10
|  |  | Delivery Cycle 1 Report draft | 7
|  |  | Game Overview | 1
|  |  | Homepage Links | 4
|  |  | Manage Leankit | 3
|  |  | Screen for new user | 2
|  |  | Stories page | 0.3
|  |  | Week 5 - Delivery Cycle 1 / presentation | 13
|  |  | Delivery Cycle 1 Report final version | 6
|  |  | Make Some Slides for DC1 | 1
|  |  | Testing DC1 | 6
|  |  | Week 5 - Delivery Cycle 2 | 61
|  |  | Collect question about the data | 16
|  |  | Collect question about the team | 6
|  |  | Contact us | 2
|  |  | Credit page in game | 3
|  |  | Game design for different levels | 6
|  |  | Game Graphics with background, other in game graphics. | 10
|  |  | Game Menu | 5
|  |  | Interesting Facts | 2
|  |  | Introduction page for the game before loading to menu | 3
|  |  | Manage Leankit | 3
|  |  | Settings | 2
|  |  | Web server with pool of questions for the game | 3
|  |  | Week 6 - Delivery Cycle 2 | 52
|  |  | Contact us page with an input form | 3
|  |  | Delivery Cycle 1 Report draft | 8
|  |  | Make conclusions about the tips and create material | 8
|  |  | Manage Leankit | 3
|  |  | Manage Statistics | 3
|  |  | Manage Website | 3
|  |  | Relevant statistics in the website | 2
|  |  | Testing DC2 | 9
|  |  | Analyse the data and make conclusions to show in the page, including graph and all reports | 13
|  |  | Grand Total | 217.3

## Data
Working Hours
Task | Week | Rocio | Archit | Shahwaz | Alvin | Team | Total
Brainstorm Project Ideas | Week2 - Planning |  |  |  |  | 2 | 2
Researching | Week2 - Planning |  |  |  |  | 5 | 5
Project decision | Week2 - Planning |  |  |  |  | 1 | 1
Brainstorm on video presentation ideas | Week2 - Planning |  |  |  |  | 2 | 2
System Overview Proposal and planning | Week2 - Planning | [5 empty] | 0
Draft System Overview Proposal Version 1 | Week2 - Planning | 4 |  |  |  |  | 4
Delivery Cycle Overview first version | Week2 - Planning |  |  |  |  | 4 | 4
Delivery Cycle planning first version | Week2 - Planning |  |  |  |  | 5 | 5
Functional Decomposition Diagram first version | Week2 - Planning |  | 2 |  | 3 |  | 5
Functional Decomposition Diagram Second Version | Week2 - Planning | 3 |  |  |  |  | 3
Executive overview | Week3 - Project Presentation | 1 | 3 |  |  |  | 4
PowerPoint for the presentation | Week3 - Project Presentation | 2 |  |  |  |  | 2
Homepage Links | Week 4 - Delivery Cycle 1 |  |  | 4 |  |  | 4
Screen for new user | Week 4 - Delivery Cycle 1 |  |  | 2 |  |  | 2
Screen for returning user | Week 4 - Delivery Cycle 1 |  |  | 2 |  |  | 2
About us’ content | Week 4 - Delivery Cycle 1 |  |  | 1 |  |  | 1
Game Overview | Week 4 - Delivery Cycle 1 |  |  | 1 |  |  | 1
Stories page | Week 4 - Delivery Cycle 1 |  |  | 0.3 |  |  | 0.3
Game: | [6 empty] | 0
Main Functionalities in each level | Week 4 - Delivery Cycle 1 |  |  | 4 |  |  | 4
Delivery Cycle 1 Report draft | Week 4 - Delivery Cycle 1 | 3 | 3 |  | 1 |  | 7
Collect and Integrate data | Week 4 - Delivery Cycle 1 |  | 10 |  | 10 |  | 20
Collect Tips and general facts | Week 4 - Delivery Cycle 1 | 10 |  |  |  |  | 10
Manage Leankit | Week 4 - Delivery Cycle 1 | 3 |  |  |  |  | 3
Delivery Cycle 1 Report final version | Week 5 - Delivery Cycle 1 / presentation | 3 | 3 |  |  |  | 6
Make Some Slides for DC1 | Week 5 - Delivery Cycle 1 / presentation | 1 |  |  |  |  | 1
Testing DC1 | Week 5 - Delivery Cycle 1 / presentation | 2 | 2 |  | 2 |  | 6
Game Menu | Week 5 - Delivery Cycle 2 |  |  | 5 |  |  | 5
Credit page in game | Week 5 - Delivery Cycle 2 |  |  | 3 |  |  | 3
Introduction page for the game before loading to menu | Week 5 - Delivery Cycle 2 |  |  | 3 |  |  | 3
Game Graphics with background, other in game graphics. | Week 5 - Delivery Cycle 2 |  |  |  | 10 |  | 10
Game design for different levels | Week 5 - Delivery Cycle 2 |  |  | 6 |  |  | 6
Web server with pool of questions for the game | Week 5 - Delivery Cycle 2 |  |  | 3 |  |  | 3
Settings | Week 5 - Delivery Cycle 2 |  |  | 2 |  |  | 2
Interesting Facts | Week 5 - Delivery Cycle 2 |  |  | 2 |  |  | 2
Contact us | Week 5 - Delivery Cycle 2 |  |  | 2 |  |  | 2
Collect question about the data | Week 5 - Delivery Cycle 2 |  | 8 |  | 8 |  | 16
Collect question about the team | Week 5 - Delivery Cycle 2 | 6 |  |  |  |  | 6
Manage Leankit | Week 5 - Delivery Cycle 2 | 3 |  |  |  |  | 3
Website | [6 empty] | 0
Analyse the data and make conclusions to show in the page, including graph and all reports | Week 6 - Delivery Cycle 2 |  | 8 |  | 5 |  | 13
Make conclusions about the tips and create material | Week 6 - Delivery Cycle 2 | 8 |  |  |  |  | 8
Contact us | [6 empty] | 0
Contact us page with an input form | Week 6 - Delivery Cycle 2 |  |  | 3 |  |  | 3
Relevant statistics in the website | Week 6 - Delivery Cycle 2 |  |  | 2 |  |  | 2
Administrator | [6 empty] | 0
Manage Website | Week 6 - Delivery Cycle 2 |  |  | 3 |  |  | 3
Manage Statistics | Week 6 - Delivery Cycle 2 |  |  | 3 |  |  | 3
Testing DC2 | Week 6 - Delivery Cycle 2 | 3 | 3 |  | 3 |  | 9
Delivery Cycle 1 Report draft | Week 6 - Delivery Cycle 2 | 5 | 3 |  |  |  | 8
Manage Leankit | Week 6 - Delivery Cycle 2 | 3 |  |  |  |  | 3
Total |  | 60 | 45 | 51.3 | 42 | 19 | 217.3